Our first Research Plan

objective

By the end of this week everyone of us should have:

- A clearly defined team structure.

- A shared understanding of PAOS.

- Four assigned research domains.

- A common literature database.

- An initial list of important scientific papers.

- A preliminary map of the PAOS research gap.

- One candidate pharmaceutical manufacturing problem for your first joint study.

No PAOS app. No AI model. No digital twin. No fancy website.

We first build the scientific foundation.

1. REGIS: Pharmaceutical Engineering

Responsibility is to establish the scientific problem that everyone else will work around.

Tasks

Task A — Study your own manifesto critically

Read the manifesto again, but this time don't read it as its author.

Read it as a reviewer.

Create a document called:

PAOS Scientific Problem Definition — V1

Answer:

- What pharmaceutical manufacturing problem are we trying to solve?

- What is "material variability"?

- What kinds of material variability exist?

- Which one could realistically be studied?

- Which manufacturing process could be studied?

- Which CQAs could be measured?

- What does "adaptation" mean?

- What does "resilience" mean?

- What would constitute manufacturing failure?

- What would constitute successful adaptation?

The output

A 2–3 page document answering those questions.

Do not worry about making it beautiful.

I want scientific thinking.

2. Paisible: DATA SCIENCE

Position

PAOS Data Science & Predictive Modeling Lead

Your job is to investigate how pharmaceutical researchers already use statistics and mathematical modeling to study material/process relationships.

Task A — Literature investigation

You should search for papers involving combinations of:

- pharmaceutical material variability

- powder properties

- formulation variability

- process modeling

- CQA prediction

- Design of Experiments

- Quality by Design

- predictive modeling

- uncertainty quantification

Task B — Build the first PAOS literature spreadsheet

Their first spreadsheet should contain:

| Paper | Year | Material | Material Attribute | Process | CQA | Statistical Method | Model | Main Finding | Limitation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Target

At least 10 serious papers tomorrow.

Not 50 low-quality Google results.

Ten papers that the student actually understands.

Task C

You should identify:

What statistical methods are most commonly used to connect material properties with pharmaceutical process/product performance?

Output tomorrow

PAOS Data Science Literature Review — V1

Approximately 1–2 pages + literature spreadsheet.

3. Amos Guy: COMPUTER SCIENCE

Position

PAOS Computational Modeling & Optimization Lead

Your task is not to start programming PAOS.

Your task is to determine what computational problems PAOS could legitimately contain.

Task A — Investigate

Search literature around:

- pharmaceutical process modeling

- pharmaceutical process simulation

- manufacturing optimization

- process control

- computational formulation

- digital twins in pharmaceutical manufacturing

- optimization under uncertainty

- pharmaceutical manufacturing decision support

Task B — Identify computational opportunities

Create a table:

| Pharmaceutical problem | Computational problem | Possible method | Required data | Expected output |
| --- | --- | --- | --- | --- |
| Material variability | Predict process response | Regression/model | Material + process data | Predicted response |
| Process adaptation | Find operating conditions | Optimization | Process constraints | Recommended conditions |
| Disturbance | Simulate scenarios | Simulation | Material distributions | Scenario outcomes |

But you must verify these concepts through literature, not simply invent them.

Task C

Answer:

What computational methods could eventually help PAOS make manufacturing adaptation decisions?

Output

PAOS Computational Research Review — V1

1–2 pages + computational-method table.

4. Gad: INFORMATION TECHNOLOGY

Position

PAOS Information Systems & Data Infrastructure Lead

Your first task is to understand the data architecture problem.

Again:

No database programming at this time.

First understand what information PAOS will eventually need.

Task A — Investigate

Research:

- pharmaceutical data management

- laboratory data management

- pharmaceutical manufacturing databases

- FAIR data principles

- scientific data reproducibility

- laboratory information management systems

- pharmaceutical manufacturing information systems

- data integrity in pharmaceutical environments

Task B — Design a conceptual PAOS database

You should create a preliminary structure for PAOS Data

The literature should determine whether it is appropriate.

Task C

Answer:

What data must PAOS eventually store to connect material properties, manufacturing conditions, CQAs, models and adaptation decisions?

Outputs

PAOS Information Architecture Review — V1

1–2 pages + preliminary database schema.

5. The Most Important Task:

After everyone completes their individual works, we will meet together.

We will have a meeting of approximately 60–90 minutes.

And we will be discussing about one question only:

What is the smallest scientifically meaningful problem that PAOS could investigate?

Everyone needs to ask himself this questions :

Pharmaceutical Engineering

What is the material property?

Data Science

How can we quantify its relationship with the process/CQA?

Computer Science

Can we computationally model or optimize the response?

Information Technology

How should the resulting data be stored and integrated?